# WEEKLY UPDATE 12th August 2019: Meat Industry Strategic Plan 2030...

Hi everyone, Project status MISP has now completely entered drafting phase in the lead up to October 2019 finalisation. A project report can be found here. This week sees a critical project phase with all MISP partners meeting in Canberra 13 - 14 August. A reminder that Tamara Badenoch is the key liaison point on this project moving forward and can be contacted on tamara@rmac.com.au. Last week (w/c 5th Aug) - August CDT meeting (6 Aug) to review further MISP drafting - Iteration of MISP based on CDT comment - Development of next MISP iteration for RMAC review - Preparation for RMAC meeting to review next MISP iteration - Continued full MISP document drafting Next week (w/c 12th Aug) - Review of next MISP iteration with combined RMAC Board/CEO meeting - Further iteration of MISP based on RMAC Board/CEO feedback - Continued full MISP document drafting Drafting and Review Schedule Please be advised in this phase of the key drafting and review dates: - 5 August – Distribute Draft Strategy + Other Materials to CDT [COMPLETE] - 6 August – CDT Review Session [COMPLETE] - 9 Aug – Draft 1 released for Board + CEOs [COMPLETE] - 13 – 14 August – Board + CEO page turn of Draft 1 - 19 August – 30 August – Next release – RMAC CEOs and Directors will be sharing with their boards and we have various stakeholder engagements locked in over this period. - 23 August – FYI ONLY: RMAC Internal Planning Day - 27 August – Distribution of materials for September CDT - 29 August – FYI ONLY: Joint Partner Communications Planning Day - 5 September – September CDT - 9 September – Final Draft released - 13 September – RMAC CEO and Board Strategy Final Review meeting - 30 September – Proposed finalisation of Final Draft - 16 October – Launch This week will be a very busy one for RMAC so your patience as ever appreciated in receiving a response! Kind Regards,...